## Sheet1
| Bastian | Sebastiaan
2011-10-31 | cascaded shadowmaps, basic saving loading, components | Sound af basic editor: model loading, transformation tools, picking, basic interface Model auto
2011-11-07
2011-11-14 | car physics | asset manager
Milestone1: basis scene
2011-11-21 | particles | entities
2011-11-28 | instancing, LOD | editor af
Mileston2: Engine af
2011-12-05 | player gameplay: shooting, shields | enemies
2011-12-12 | speler 2: turret | gui (menu, upgrades)
2011-12-19 | upgrade slots | extra wapens
2011-12-26 | kerstmis vieren, veel eten, pakjes opendoen | 3d shit + debugging
2012-01-02 | debugging | debugging